## Sheet1
Week | Duration | Work to do
1 | 10th May to 16th May | • Designing the website on figma and setting up the theme of the website. • Connecting with URL team and make the wesbite start working • Getting all the links to publications and talks which were not working before. • Get reflections for the first essay
2 | 17th May to 23rd May | • Designing the contact tab and the main home page and finish the final page by the end of the week. • Start writing the second essay
3 | 24th May to 30th May | • Designing the practise and travel tab and finish the final page by the end of the week. • Get reflections for the second essay.
4 | 31st May to 6th June | • Designing the research and people tab and finish the final page by the end of the week. • Start writing the third essay • Start designing my personal website
5 | 7th June to 13th June | • Designing the Resume and Teaching tab and finish the final page by the end of the week. • Get reflections for the third essay • Starting my work on my personal website
6 | 14th June to 20th June | • Designing the Passion, Reaction and Talks and finish the final page by the end of the week. • Start writing the fourth essay • Deploying and scaling of my personal website
7 | 21st June to 27th June | • Deploying the website and testing the scalability and also how much load can it take for the website. • Get reflections for the fourth essay. • Get reflections for my personal website.